## project
Project Planner
[10 empty] | Period Highlight: |  |  |  |  | 2016-05-09 12:35 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
|  | PLAN | Optimistic | Realistic | Pessimistic | ACTUAL | ACTUAL | PERCENT | Team
ACTIVITY | prerequisite | START | DURATION | DURATION | DURATION | START | DURATION | COMPLETE | Member | PERIODS
 | time axis 2016-03-23 to 2016-05-07
Get the extension basics up and running, like browser icon, manifest etc. |  | 2016-03-23 | 1 | 3 | 5 | 2016-03-25 | 3 | 100% | Dylan
Get timer running when start is Pressed |  | 2016-03-23 | 1 | 3 | 5 | 2016-03-25 | 3 | 100% | Dylan
Make databases to store websites |  | 2016-03-27 | 1 | 3 | 5 | 2016-04-02 | 1 | 100% | Sri
Make customizable settings page to set the websites to block and store in different table in database |  | 2016-03-27 | 1 | 3 | 5 | 2016-04-02 | 1 | 100% | Sri
Grab URL of active tab and check is it’s in blacklist |  | 2016-03-27 | 2 | 3 | 6 | 2016-04-04 | 2 | 100% | Sri
Pop-up if in bad website is active. Redirect to google if pressed cancel. If OK, start the bad timer |  | 2016-03-25 | 1 | 3 | 5 | 2016-03-29 | 6 | 100% | Luke D
Get the front-end developed, new tab should be customized |  | 2016-03-25 | 2 | 4 | 6 | 2016-03-29 | 4 | 100% | Vuong
Create productivity graphs |  | 2016-03-30 | 1 | 3 | 5 | 2016-04-03 | 4 | 100% | Luke W
learn front frame work |  | 2016-04-08 | 1 |  |  | 2016-04-08 | 0 | 0% | Luke W
Set to-do list and be able to delete them when done |  | 2016-04-18 | 1 |  |  | 2016-04-09 | 0 | 100% | Vuong
create storage for daily to-do list. |  | 2016-04-10 | 1 |  |  | 2016-04-10 | 0 | 0% | Luke W
Improve front end |  | 2016-04-15 | 3 | 4 | 5 | 2016-04-11 | 0 | 75% | Vuong
research reference extensions |  | 2016-04-11 | 4 | 5 | 6 | 2016-04-11 | 5 |  | Luke W
Make storage for daily productivity graph |  | 2016-04-15 | 4 | 5 | 6 |  |  |  | Luke D
bad timer improvement based on sites |  | 2016-04-15 | 4 | 6 | 8 |  |  |  | Dylan
Make daily productivity graph. |  | 2016-04-22 | 4 | 5 | 6 |  |  |  | Luke D
Create graph for specificific website usage. |  | 2016-04-22 | 4 | 5 | 6 |  |  |  | Luke D
share graph on facebook twitter, etc | [8 empty] | Sri
create stars | [8 empty] | Sri
pop up/alert blur (block site) |  | 2016-04-22 | 4 | 5 | 6
testing!!!! |  | 2016-04-11 | 21 | 21 | 21
browser bot |  | 2016-04-15 | 10 | 14 | 20 |  |  |  | Luke W
pop up/drop down styling |  | 2016-04-22 | 3 | 4 | 5 |  |  | 50% | Vuong
custom user blocked websites | [8 empty] | Sri
class diagram |  | 2016-04-29 | 1 | 2 | 3
user diagram |  | 2016-04-29 | 1 | 2 | 3
state diagram
user manual |  | 2016-04-29 | 2 | 3 | 4 |  |  |  | Luke D
deployment strategy |  | 2016-04-29 | 2 | 3 | 4 |  |  |  | Dylan
maintance plan

## Sheet1
Sri | 0% | Product backlog
Vuong | 25% | Get the extension basics up and running, like browser icon, manifest etc.
Luke D | 50% | Get timer running when start is Pressed
Luke W | 75% | Make databases to store websites
Dylan | 100% | Make customizable settings page to set the websites to block and store in different table in database
Grab URL of active tab and check is it’s in blacklist
Pop-up if in bad website is active. Redirect to google if pressed cancel. If OK, start the bad timer
Get the front-end developed, new tab should be customized
Analyze data and develop stats and graphs and display it in new tab
Make better productivity stats ad graphs
Pop-up appropriate messages for goals to be completed
User can input his/her own websites
Give flexible time to block websites.
Document the extension well.
Set to-do list and be able to delete them when done
customize our app further to make it look better and easy to use.
Improve the backend and speed with client-side JavaScript framework
learn node.js
learn front frame work
Make daily productivity graph.
Make storage for daily productivity graph
Update timer to track specific websites
Create graph for specificific website usage.
create storage for daily to-do list.
abiltity todo list
reminder for todo list pop up
todo list time
research grunt js or other testing software
testing
Improve front end
share data on Facebook, twitter, etc.